## CobiT RACI
Continual Service Improvement RACI Matrix | Governence Board | IT Executive Committee | CIO | Business Executive | IT Managers | IT Process Owners | IT Audit | Risk & Compliance | Programme Steering
Phase 1—What Are the Drivers?
Identify issues triggering need to act | C/I | A | R | R | C | C | C | C | R
Identify business priorities and strategies affecting IT | C | A | R | R | C | C | C | C | R
Gain management agreement to act and obtain executive sponsorship | C | A/R | R | C | I | I | I | I | R
Instil the appropriate level of urgency to change | I | A | R | R | C | C | C | C | R
Produce convincing outline business case | I | A | R | C | C | C | C | C | R
Phase 2—Where Are We Now?
Identify key IT goals supporting business goals | I | C | R | C | R | C | C | C | A
Identify processes critical to support IT and business goals |  | I | R | C | R | C | C | C | A
Assess risk related to achievement of goals |  | I | R | C | R | R | C | R | A
Identify processes critical to ensure that key risk is avoided |  | I | R | R | R | C | C | R | A
Assess current performance of critical processes |  | I | R | C | R | R | C | C | A
Assemble a core team from the business and IT |  | I | R | R | C | C | C | C | A
Review and evaluate the business case | I | A | R | R | C | C | C | C | R
Phase 3—Where Do We Want To Be?
Agree on target for improvement | I | A | R | C | R | R | C | C | R
Analyse gaps |  | I | R | C | R | R | C | C | A
Identify potential improvements |  | I | R | C | R | R | C | C | A
Communicate change vision |  | A | R | R | C | I | I | I | R
Set programme direction and prepare detailed business case | I | A | R | C | C | C | I | I | R
Phase 4—What Needs To Be Done?
Priorities and select improvements |  | A | R | C | C | R | C | C | R
Define and justify projects |  | I | R | C | R | R | C | C | A
Design change response plans |  | I | R | R | C | C | C | C | A
Identify quick wins and build on existing strengths |  | I | C | C/I | R | R | C/I | C/I | A
Develop programme plan with allocated resources and project plans |  | A | C | C | R | C | I | I | R
Phase 5—How Do We Get There?
Develop and, if required, acquire solutions |  | A | C | C | R | R | C | C | R
Adopt and adapt best practices |  | I | R | C | R | R | C | C | A
Test and roll out solutions |  | I | R | C | R | R | C | C | A
Capitalise on quick wins |  | I | C | C/I | R | R | C/I | C/I | A
Implement change response plans | I | I | R | C | R | R | I | I | A
Direct and monitor projects within the programme | I | A | C | C | R | C | I | I | R
Phase 6—Did We Get There?
Operate the solutions and gain performance feedback |  | I | A | R | R | R | I | I | I
Monitor performance against success metrics |  | I | A | C | R | R | C | C | I
Communicate positive and negative results | I | I | A | C | R | C | I | I | I
Monitor ownership of roles and responsibilities |  | A | R | C | C | C | C | C | I
Monitor programme results (achievement of goals and realisation of benefits) | I | A | C | C | C | C | C | C | R
Phase 7—How Do We Keep the Momentum Going?
Identify new governance objectives | C | A | R | R | C | C | C | C | I
Identify lessons learned |  | I | A | C | R | R | C | C | I
Sustain and reinforce changes |  | A | R | R | R | R | C | C | I
Confirm conformance to objectives and requirements | I | A | R | C | R | R | R | I | R
Close programme with formal review of effectiveness | I | A | C | C | C | C | C | C | R